## obs构建 (hidden)
任务组 | 任务 | 任务描述 | 行动方案 | 责任人 | 时间要求 | 完成状态 | 备注 | 计划开始日期 | 计划完成日期 | 实际开始时间 | 实际完成时间
[meta] 解决RISC-V的构建失败问题 | OBS构建学习 | 了解项目现状、目标、任务
本项目obs构建架构
会查看构建的信息、构建错误、错误日志，能够对错误日志进行分析；
完成openEuler RISC-V 本地环境搭建
| OBS构建上手 | 寻找一个构建成功的包，每人都尝试按照流程进行构建； | 定义一个包+fork到rv_spare仓中 | 马驰
|  |  | 从rv_spare仓中fork到个人仓库，并进行本地osc构建 | all
|  | 找一个问题容易解决的包，每人都尝试去解决这个包的问题，相互构沟通，完成和解决包的问题； | 定义一个包+fork到rv_spare仓中 | 马驰
|  |  | 从rv_spare仓中fork到个人仓库，对问题进行分析、修改，本地osc构建 | all
| OBS构建任务 | 每人分别去认领一个构建失败的包（从简单的开始），分别去分析和解决所负责的包的问题；
| D1上运行openEuler |  |  | 王翔 | 2021-08-31
| bishengJDK |  |  | 王俊强 | 2021-08-31
| openEuler图形界面支持 |  | 先找一个GUI的包安装，看还缺少什么包 |  | 2021-08-31
| D1+openEuler+bishengJDK+JavaDemo |  |  |  | 2021-09-15 | 等待输入

## excluded 396
修改说明： 1. 对于ExclusiveArch 没有riscv64的，在该字段后面添加riscv64；目的是让obs构建在riscv64下能够执行构建（不论构建结果是成功还是失败） 2. ExclusiveArch包含noarch 的spec文件，不用修改了，该类型包先跳过。 3. 启动构建后，构建成功的提交PR
excluded | 完成情况 | 修改后构建结果 | 说明
acpid | 成功启动构建 | successed
arm-trusted-firmware | 成功启动构建 | failed
biosdevname | 成功启动构建 | failed
bpftrace | 成功启动构建 | unresolvable
coffee-script |  | ExclusiveArch: noarch
color-filesystem | 成功启动构建 | successed
ComputeLibrary | 成功启动构建 | failed
criu | 成功启动构建 | unresolvable
dmidecode | 成功启动构建 | successed
docker-anaconda-addon | 成功启动构建 | successed
dpdk | 成功启动构建 | failed
dyninst | 成功启动构建 | failed
edac-utils | 成功启动构建 | succeeded
efibootmgr | 成功启动构建 | succeeded
gnome-boxes | 成功启动构建 | unresolvable
gnu-efi | 成功启动构建 | failed
golang | 成功启动构建 | unresolvable
guacamole | 未能启动构建 | 源码仓里没有代码
intel-cmt-cat | 成功启动构建 | failed
intel-sgx-ssl | 成功启动构建 | unresolvable
iSulad | 成功启动构建 | unresolvable
itrustee_sdk | 成功启动构建 | succeeded
kae_driver | 成功启动构建 | failed
kmod-kvdo | 成功启动构建 | failed | can't exec brp-digest-list
latrace | 成功启动构建 | failed
lcr | 成功启动构建 | unresolvable | 依赖lxc failed
libipt | 成功启动构建 | succeeded
libkae | 成功启动构建 | unresolvable | 依赖libwd 构建excluded
libsmbios | 成功启动构建 | unresolvable | 依赖valgrind 构建failed
libunwind | 成功启动构建 | failed
libwd | 成功启动构建 | failed
libxsmm | 成功启动构建 | unresolvable | 依赖openblas 构建excluded
linux-sgx | 成功启动构建 | unresolvable | 依赖ocaml 构建unresolvable
linux-sgx-driver | 成功启动构建 | failed
luajit | 成功启动构建 | failed
lwip | 成功启动构建 | succeeded
mcelog | 成功启动构建 | succeeded
memkind | 成功启动构建 | failed
microcode_ctl | 成功启动构建 | succeeded
mocha | 成功启动构建 | 没有修改 noarch
mongodb | 成功启动构建 | unresolvable
nvml | 成功启动构建 | unresolvable
oneDNN | 成功启动构建 | failed
opa-psm2 | 成功启动构建 | failed
openblas | 成功启动构建 | failed
openjfx11 | 成功启动构建 | unresolvable
openjfx8 | 成功启动构建 | unresolvable
prefetch_tuning | 成功启动构建 | failed | error: asm/types.h: No such file or directory
psm | 成功启动构建 | failed | Bad exit status from /var/tmp/rpm-tmp.wd2IiA (%build)
rear | 成功启动构建 | failed | error: Couldn't exec /usr/lib/rpm/openEuler/brp-digest-list: No such file or directory
rpm-ostree | 成功启动构建 | unresolvable | nothing provides cargo
rust | 成功启动构建 | unresolvable | nothing provides cargo >= 1.50.0, nothing provides (rust >= 1.50.0 with rust <= 1.51.0), nothing provides musl-libc-static, nothing provides musl-gcc, nothing provides llvm >= 9.0, nothing provides llvm-devel >= 9.0
sgabios | 成功启动构建 | failed | error: Bad exit status from /var/tmp/rpm-tmp.EYcJ7j (%build)
shim | 成功启动构建 | unresolvable | nothing provides gnu-efi, nothing provides gnu-efi-devel
spark | 成功启动构建 | unresolvable | nothing provides java-1.8.0-openjdk-devel, nothing provides maven
spdk | 成功启动构建 | unresolvable | nothing provides dpdk-devel, nothing provides libibverbs-devel, nothing provides librdmacm-devel
spice | 成功启动构建 | unresolvable | nothing provides libcacard-devel
stratovirt | 成功启动构建 | unresolvable | nothing provides rust, nothing provides cargo, nothing provides rust-packaging
syslinux | 成功启动构建 | failed | Bad exit status from /var/tmp/rpm-tmp.ob2sSa (%build)
tboot | 成功启动构建 | failed
uglify-js
uglify-js1
vboot-utils | 成功启动构建 | failed
xorg-x11-drv-intel | 成功启动构建 | unresolvable | nothing provides xorg-x11-server-devel
xorg-x11-drv-vesa | 成功启动构建 | unresolvable | nothing provides xorg-x11-server-devel >= 1.10.99.902
xorg-x11-drv-vmware | 成功启动构建 | unresolvable | nothing provides xorg-x11-server-devel >= 1.10.99.902
node-gyp
node_exporter
nodejs-abbrev
nodejs-acorn
nodejs-ansi
nodejs-ansi-font
nodejs-ansi-regex
nodejs-ansi-styles
nodejs-are-we-there-yet
nodejs-argparse
nodejs-array-differ
nodejs-array-index
nodejs-array-union
nodejs-array-uniq
nodejs-arrify
nodejs-asap
nodejs-asn1
nodejs-assert-plus
nodejs-assertion-error
nodejs-async
nodejs-aws-sign2
nodejs-balanced-match
nodejs-better-assert
nodejs-bindings
nodejs-bl
nodejs-block-stream
nodejs-bluebird
nodejs-boom
nodejs-brace-expansion
nodejs-buffer-equal
nodejs-builtin-modules
nodejs-bunker
nodejs-burrito
nodejs-bytes
nodejs-caller-callsite
nodejs-caller-path
nodejs-callsite
nodejs-callsites
nodejs-caseless
nodejs-chai
nodejs-chalk
nodejs-character-parser
nodejs-charm
nodejs-cjson
nodejs-clean-css
nodejs-cli-color
nodejs-closure-compiler
nodejs-colors
nodejs-combined-stream
nodejs-commander
nodejs-commonmark
nodejs-concat-map
nodejs-concat-stream
nodejs-console-dot-log
nodejs-constantinople
nodejs-core-util-is
nodejs-cryptiles
nodejs-css
nodejs-css-parse
nodejs-css-stringify
nodejs-d
nodejs-dateformat
nodejs-debug
nodejs-deep-eql
nodejs-deep-equal
nodejs-deep-is
nodejs-defence
nodejs-defence-cli
nodejs-define-properties
nodejs-defined
nodejs-delayed-stream
nodejs-delegates
nodejs-diff
nodejs-difflet
nodejs-difflib
nodejs-docopt
nodejs-dreamopt
nodejs-duplexer
nodejs-ebnf-parser
nodejs-ejs
nodejs-end-of-stream
nodejs-entities
nodejs-es-abstract
nodejs-es-to-primitive
nodejs-es5-ext
nodejs-es6-iterator
nodejs-es6-symbol
nodejs-es6-weak-map
nodejs-escape-string-regexp
nodejs-escodegen
nodejs-esprima
nodejs-estraverse
nodejs-esutils
nodejs-event-emitter
nodejs-eventemitter2
nodejs-events-to-array
nodejs-exit
nodejs-expect-dot-js
nodejs-extend
nodejs-eyes
nodejs-fast-levenshtein
nodejs-faye-websocket
nodejs-figures
nodejs-fileset
nodejs-fill-keys
nodejs-find-up
nodejs-findup-sync
nodejs-flot
nodejs-for-each
nodejs-foreach
nodejs-forever-agent
nodejs-form-data
nodejs-formatio
nodejs-from
nodejs-fstream
nodejs-function-bind
nodejs-gauge
nodejs-gaze
nodejs-generate-function
nodejs-generate-object-property
nodejs-getobject
nodejs-github-url-from-git
nodejs-glob
nodejs-globule
nodejs-graceful-fs
nodejs-graceful-readlink
nodejs-growl
nodejs-grunt
nodejs-grunt-cli
nodejs-grunt-contrib-clean
nodejs-grunt-contrib-internal
nodejs-grunt-contrib-nodeunit
nodejs-grunt-contrib-uglify
nodejs-grunt-contrib-watch
nodejs-grunt-known-options
nodejs-grunt-legacy-log
nodejs-grunt-legacy-log-utils
nodejs-grunt-legacy-util
nodejs-gzip-size
nodejs-handlebars
nodejs-har-validator
nodejs-has
nodejs-has-ansi
nodejs-has-color
nodejs-has-flag
nodejs-has-symbols
nodejs-has-unicode
nodejs-hash_file
nodejs-hawk
nodejs-heap
nodejs-hoek
nodejs-hooker
nodejs-hosted-git-info
nodejs-http-signature
nodejs-iconv
nodejs-iconv-lite
nodejs-image-size
nodejs-inflight
nodejs-inherits
nodejs-inherits1
nodejs-interpret
nodejs-is
nodejs-is-builtin-module
nodejs-is-callable
nodejs-is-date-object
nodejs-is-function
nodejs-is-my-json-valid
nodejs-is-object
nodejs-is-property
nodejs-is-regex
nodejs-is-symbol
nodejs-is-typedarray
nodejs-isarray
nodejs-isexe
nodejs-isstream
nodejs-istanbul
nodejs-jade
nodejs-jison
nodejs-jison-lex
nodejs-jju
nodejs-js-yaml
nodejs-json-diff
nodejs-json-parse-helpfulerror
nodejs-json-stringify-safe
nodejs-jsonify
nodejs-jsonpointer
nodejs-jsonselect
nodejs-less
nodejs-less-plugin-clean-css
nodejs-levn
nodejs-lex-parser
nodejs-load-grunt-tasks
nodejs-locate-path
nodejs-lolex
nodejs-lru-queue
nodejs-make-arrow-function
nodejs-make-generator-function
nodejs-maxmin
nodejs-mdurl
nodejs-memoizee
nodejs-merge-descriptors
nodejs-mime
nodejs-mime-db
nodejs-mime-types
nodejs-minimatch
nodejs-minimist
nodejs-mkdirp
nodejs-mock-fs
nodejs-module-not-found-error
nodejs-monocle
nodejs-ms
nodejs-multimatch
nodejs-nan
nodejs-nan0
nodejs-nan1
nodejs-next-tick
nodejs-node-uuid
nodejs-nomnom
nodejs-nopt
nodejs-noptify
nodejs-normalize-package-data
nodejs-npmlog
nodejs-oauth-sign
nodejs-object-assign
nodejs-object-dot-assign
nodejs-object-inspect
nodejs-object-is
nodejs-object-keys
nodejs-once
nodejs-optionator
nodejs-os-homedir
nodejs-os-tmpdir
nodejs-osenv
nodejs-p-limit
nodejs-p-locate
nodejs-package
nodejs-paperboy
nodejs-path-array
nodejs-path-exists
nodejs-path-is-absolute
nodejs-path-parse
nodejs-pinkie
nodejs-pinkie-promise
nodejs-pkg-up
nodejs-prelude-ls
nodejs-pretty-bytes
nodejs-process-nextick-args
nodejs-promise
nodejs-promises-aplus-tests
nodejs-proxyquire
nodejs-qs
nodejs-raw-body
nodejs-read-package-json
nodejs-readable-stream
nodejs-readdirp
nodejs-rechoir
nodejs-replace-require-self
nodejs-request
nodejs-require-directory
nodejs-require-inject
nodejs-require-uncached
nodejs-requirejs
nodejs-resolve
nodejs-resolve-from
nodejs-resolve-pkg
nodejs-resumer
nodejs-rimraf
nodejs-rollup
nodejs-runforcover
nodejs-safe-buffer
nodejs-samsam
nodejs-semver
nodejs-set-immediate-shim
nodejs-shelljs
nodejs-should
nodejs-should-equal
nodejs-should-format
nodejs-should-type
nodejs-simple-assert
nodejs-sinon
nodejs-slide
nodejs-sntp
nodejs-source-map
nodejs-source-map-support
nodejs-spdx-correct
nodejs-spdx-exceptions
nodejs-spdx-expression-parse
nodejs-spdx-license-ids
nodejs-sprintf-js
nodejs-stream-replace
nodejs-string
nodejs-string-dot-prototype-dot-repeat
nodejs-string-dot-prototype-dot-trim
nodejs-string_decoder
nodejs-stringstream
nodejs-strip-ansi
nodejs-strip-json-comments
nodejs-supports-color
nodejs-tap
nodejs-tap-parser
nodejs-tape
nodejs-tar
nodejs-temporary
nodejs-test
nodejs-through
nodejs-through2
nodejs-timers-ext
nodejs-tiny-lr-fork
nodejs-tough-cookie
nodejs-transformers
nodejs-traverse
nodejs-tunnel-agent
nodejs-type-check
nodejs-type-detect
nodejs-underscore
nodejs-unpipe
nodejs-uri-path
nodejs-util
nodejs-util-deprecate
nodejs-validate-npm-package-license
nodejs-vows
nodejs-websocket-driver
nodejs-which
nodejs-window-size
nodejs-with
nodejs-wordwrap
nodejs-wrappy
nodejs-xtend
nodejs-yargs
nodeunit

## broken 21
说明： 1. broken状态的包大多是因为_service文件导致的未启动构建 2. openEuler:Mainline:RISC-V—broken下的包 （1） Branch package（部分包需要点Show unmerged sources 才能看到 Branch package） （2）随便下载一个_service文件（或者新建一个），然后修改url、revision信息；url一般最先使用src-openeuler下对应的源；revision用包对应repo的最新commitID （3）在个人obs对应的包界面，add file中选择已经编辑好的_service文件 3. 观察是否启动构建，记录最后的构建状态； 4. 最后将构建成功的包，由xijing一起统计后提交到大群；构建不成功的，内部再进一步分析；
broken | 构建结果 | 备注
assimp | succeeded
boost | unresolvable | nothing provides python3-numpy
containerd | unresolvable | nothing provides subversion needed by golang
docker | unresolvable | nothing provides selinux-policy, nothing provides selinux-policy-devel, nothing provides containerd, nothing provides docker-runc, nothing provides subversion needed by golang
efl
erlang-eflame
geos | succeeded
ghostscript | failed
glassfish-dtd-parser | unresolvable
glassfish-hk2 | unresolvable | nothing provides mvn(aopalliance:aopalliance), nothing provides mvn(javax.annotation:javax.annotation-api), nothing provides mvn(javax.enterprise:cdi-api), nothing provides mvn(javax.inject:javax.inject), nothing provides mvn(junit:junit), nothing provides mvn(org.apache.ant:ant), nothing provides mvn(org.apache.commons:commons-lang3), nothing provides mvn(org.apache.felix:maven-bundle-plugin), nothing provides mvn(org.apache.maven:maven-core), nothing provides mvn(org.apache.maven:maven-plugin-api), nothing provides mvn(org.apache.maven.plugins:maven-plugin-plugin), nothing provides mvn(org.apache.maven.shared:maven-osgi), nothing provides mvn(org.easymock:easymock), nothing provides mvn(org.javassist:javassist), nothing provides mvn(org.osgi:osgi.cmpn), nothing provides mvn(org.osgi:osgi.core), nothing provides mvn(org.ow2.asm:asm-all), nothing provides mvn(args4j:args4j), nothing provides mvn(com.google.inject:guice), nothing provides mvn(com.google.protobuf:protobuf-java), nothing provides mvn(javax.el:javax.el-api), nothing provides mvn(javax.json:javax.json-api), nothing provides mvn(javax.validation:validation-api), nothing provides mvn(javax.xml.bind:jaxb-api), nothing provides mvn(org.apache.bcel:bcel), nothing provides mvn(org.apache.felix:org.apache.felix.bundlerepository), nothing provides mvn(org.apache.maven.plugins:maven-antrun-plugin), nothing provides mvn(org.apache.maven.plugins:maven-dependency-plugin), nothing provides mvn(org.assertj:assertj-core), nothing provides mvn(org.glassfish:javax.json), nothing provides mvn(org.hibernate:hibernate-validator), nothing provides mvn(org.mockito:mockito-core), nothing provides mvn(org.springframework:spring-context), nothing provides mvn(org.testng:testng), nothing provides mvn(junit:junit) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-compiler-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-jar-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-javadoc-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-resources-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-surefire-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.surefire:surefire-junit4) needed by maven-local, nothing provides mvn(org.apache.maven.surefire:surefire-testng) needed by maven-local, nothing provides xmvn-connector-aether needed by maven-local, nothing provides xmvn-minimal needed by maven-local, nothing provides xmvn-mojo needed by maven-local
google-droid-fonts | building | 本来构造的时候是失败的，但张旭舟老师好像刚刚在obs上进行了提交
isula-build | unresolvable | nothing provides subversion needed by golang
kata-containers
kata_integration | excluded | spec中%build等为空
libX11 | failed
log4j | unresolvable | catalina), nothing provides mvn(org.eclipse.jetty:jetty-util), nothing provides mvn(org.eclipse.persistence:javax.persistence), nothing provides mvn(org.jboss.spec.javax.jms:jboss-jms-api_1.1_spec), nothing provides mvn(org.lightcouch:lightcouch), nothing provides mvn(org.zeromq:jeromq), nothing provides mvn(junit:junit) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-compiler-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-jar-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-javadoc-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-resources-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.plugins:maven-surefire-plugin) needed by maven-local, nothing provides mvn(org.apache.maven.surefire:surefire-junit4) needed by maven-local, nothing provides mvn(org.apache.maven.surefire:surefire-testng) needed by maven-local, nothing provides xmvn-connector-aether needed by maven-local, nothing provides xmvn-minimal needed by maven-local, nothing provides xmvn-mojo needed by maven-local
nodejs-clone | excluded | ExclusiveArch:%{nodejs_arches} noarch 所以我也没有修改
openEuler-indexhtml | unresolvable | nothing provides ncurses-base = 6.2-1.oe1 needed by ncurses-libs
openEuler-logos | broken
perl-B-Keywords | succeeded | 什么都没做，构建成功
runc | unresolvable | nothing provides subversion needed by golang